## Gantt Chart
Color code: | Blue: in progress | Green: complete | Red: problem | Grey: uncertain (future)
Capstone team (Baraa, Eddie, Manuel and Priyanshu) | Sep 20 - Sep 24 | Sep 27 - Oct 1 | Oct 4 - Oct 8 | Oct 11 - Oct 15 | Oct 18 - Oct 22 | Oct 25 - Oct 29 | Nov 1 - Nov 5 | Nov 8 - Nov 12 | Nov 15 - Nov 19 | Nov 22 - Nov 26 | Nov 29 - Dec 3 | Dec 6 - Dec 10 | Dec 13 - Dec 17
IMPORTANT DEADLINES | [12 empty] | Project Design Submission
Establish Management System
Preliminary Python Code
Testing Code
Migrate Code to Omniverse
Testing in Omniverse
Project Design Document Finalization

## WBS
Library Robot
Stage | Task | Duration | Planned dates
|  |  | Start | End
1. Research On Existing Projects | 1.1 Review exisiting algorithms for navigation using reinforcement learning | 10 | 2022-09-02 | 2022-09-22
| 1.2 Review existing methods for simulating a 3D enviroment on omniverse | 10 | 2022-09-02 | 2022-09-22
| 1.3 Review existing methods for grasping | 7 | 2022-09-16 | 2022-09-23
| 1.4 Identify the problem statement and delegate each tasks to group members to focus in | 9 | 2022-09-23 | 2022-09-30
| 1.5 Decompose the tasks needed to solve the problem and delegate to group members | 9 | 2022-09-24 | 2022-10-01
2. Plan Implementation | 2.1 Look into possible simulation enviroments | 7 | 2022-10-01 | 2022-10-07
| 2.2 Look into possible way to assemble all of the parts into one working robot | 7 | 2022-09-30 | 2022-10-07
| 2.3 Look into hardware sensors needed for the best performance | 6 | 2022-10-01 | 2022-10-07
| 2.4 Request devices needed | 3 | 2022-10-07 | 2022-10-10
| 2.5 Regroup member's individual research and select best concept design | 7 | 2022-10-08 | 2022-10-14
3. System Development | 3.1 Get simple version of your task running for a place to start with | 14 | 2022-10-14 | 2022-10-28
| 3.2 Identify Improvements to be done | 2 | 2022-10-28 | 2022-10-30
| 3.3 Perform improvements to the algorithms and system | 19 | 2022-10-30 | 2022-11-18
4. Build Software Prototype | 4.1 Build a simulation platform | 7 | 2022-11-18 | 2022-11-25
| 4.2 Integrate the seperate portions to create one simulation | 7 | 2022-11-25 | 2022-12-02
| 4.3 Test the simulation | 7 | 2022-12-02 | 2022-12-09
5. Test Software Prototype | 5.1 Develop testing criteria for possible hardware implementation | 5 | 2023-01-22 | 2023-01-27
| 5.2 Perform tests | 7 | 2023-01-27 | 2023-02-03
6. Build Hardware Model | 6.1 Build hardware model | 7 | 2023-02-03 | 2023-02-10
| 6.2 Test sensors | 5 | 2023-02-03 | 2023-02-08
| 6.3 Train model | 14 | 2023-02-10 | 2023-02-24
| 6.4 Test and refine model | 21 | 2023-02-24 | 2023-03-17
7. Document and report | 7.1 Document design process | 8 | 2023-03-16 | 2023-03-24
| 7.2 Refine analysis and proposed solution | 6 | 2023-03-24 | 2023-03-30
| 7.3 Prepare final report | 12 | 2023-04-01 | 2023-04-12
| 7.4 Prepare poster | 7 | 2023-04-12 | 2023-04-19

## Sheet3
Library Robot
TASK |  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T
1.0 Abstract Of the Project | A | bar: A
2.1 Problem analysis | B | bar: A to B
2.2 Black-box | C | bar: B to C
2.3 Problem statement | D | bar: B; D
4.1 Background Research | E | bar: B; D to E
4.2 Concept Generation | F | bar: D to F
4.3 Concept Selection | G | bar: D to H
5.1 Modeling | H | bar: G to K
5.2 Optimization | I | bar: G to I; K to L
6.1 Initial design proposed | J | bar: H to K
6.2 Changes made to initial design | K | bar: J to N
7.0 Budget | L | bar: G; J to L; O to P
8.1 Description of success | M | bar: H to I; K; M; O to P
8.2 Issues faced | N | bar: H to K; M to O; Q
8.3 Changes made | O | bar: G; I to J; N to P
8.4 initial result | P | bar: P
9.0 Ethics | Q | bar: B; E; Q
10.1 Criteria for testing | R | bar: P; R
10.2 Test Data | S | bar: R to S
10.3 Discussion on testing data | T | bar: S to T